NETWORK BUILD SERVICES SCHEDULE

entered into between

| Customer |  |
| --- | --- |
| Name | Fibertime Networks Proprietary Limited |
| Registration number | 2021/997793/07 |
| Contact Person |  |
| Physical Address | 1st Floor Oude Bank, 8 Bird Street, Stellenbosch, 7600 |
| Email Address | accounts@fibertime.com |
| Service Provider |  |
| Name |  |
| Registration number |  |
| Contact Person |  |
| Physical Address |  |
| Email Address |  |
| Service Schedule Effective Date |  |
| Service Schedule Term |  |

TABLE OF CONTENTS

Clause number and description	Page

1.	INTRODUCTION	3

2.	CANCELLATION AND REPLACEMENT OF THE ORIGINAL SERVICE SCHEDULE	3

3.	DURATION OF SERVICE SCHEDULE	3

4.	SCOPE OF THE SERVICES	4

5.	STANDARD OF PERFORMANCE	4

6.	FEES	5

APPENDIX A PROJECT SCHEDULE	7

APPENDIX B COMPLETION CHECKLIST	9

APPENDIX C APPROVED SUPPLIER LIST	19

APPENDIX D CUSTOMER CODE OF CONDUCT FOR SERVICE PROVIDERS	21

- INTRODUCTION

  - This Service Schedule sets out the terms that will apply to the Service Provider's provision of network build component of the Services to the Customer.

  - This Service Schedule is concluded in terms of the Master Service Agreement entered into by and between the Parties.

  - Capitalised terms contained in the Master Service Agreement, but which are not defined herein, shall bear the meaning ascribed thereto in the Service Agreements.

- CANCELLATION AND REPLACEMENT OF THE ORIGINAL SERVICE SCHEDULE

  - The Parties hereby agree to cancel the Original Service Schedule and to replace it with this Service Schedule. For the avoidance of doubt, this Service Schedule supersedes and replaces the Original Service Schedule and all prior commitments, undertakings and representations, whether oral or written, between the Parties (and other persons, as may be applicable) in respect of the subject matter hereof. Such supersession shall be retrospective to [insert signature date of the Original Service Schedule] and shall accordingly be deemed to have taken place on that date. This Service Schedule shall accordingly be binding on the Parties in accordance with its terms and conditions.

  - For the purpose of this clause 2, "Original Service Schedule" means the Service Schedule concluded between the Customer and the Service Provider on or about [●].

- DURATION OF SERVICE SCHEDULE

  - This Service Schedule will commence on the Service Schedule Effective Date and shall endure until terminated in according with the provisions of this Service Schedule or the Master Service Agreement.

  - At the end of the Service Schedule Term, the Service Schedule shall continue on a month-to-month basis until terminated by either Party on 30 (thirty) days prior written notice to the other Party, in which case the date of termination will be the date of receipt of the notice of termination by the relevant Party.

  - For the avoidance of doubt, any expiry or termination of this Service Schedule does not affect any rights of the Parties which may have accrued before the date of expiry or termination of the Service Schedule.

  - "Service Level Termination Event"

    - In addition to any other termination rights available to the Customer under this Service Schedule, the Customer shall have the right to terminate this Service Schedule, in whole or in part, on written notice to the Service Provider, if the Service Provider fails to remedy continuous poor performance and/or fails to achieve a minimum average of 80 (eighty) Connected Dwellings per day, within 14 (fourteen) calendar days after receipt of a written notice from the Customer specifying the performance deficiencies and stating the Customer’s dissatisfaction with the Service Provider’s performance (“Service Level Termination Event”).

    - For the purposes of this clause, "continuous poor performance" shall include, but not be limited to, repeated failure to meet agreed service levels, delays in deployment, or failure to deliver results materially in accordance with the timelines or key performance indicators specified in this Service Schedule or any annexed service schedule.

    - Termination under this clause shall be without prejudice to any other rights or remedies available to the Customer, in terms of this Service Schedule, the Master Service Agreement or otherwise, including the right to claim damages or performance guarantees where applicable.

- SCOPE OF THE SERVICES

  - As of the Service Schedule Effective Date, the Service Provider shall carry out the Services:

    - within the timeframes and milestones set out in the Project Schedule attached hereto as Appendix A;

    - in accordance with the Customer Specifications provided by the Customer to the Service Provider in writing; and

    - in compliance with the Customer Code of Conduct attached hereto as Appendix D, as may be updated from time to time by the Customer;

- all as read with and in compliance with the terms and conditions contained in the Master Service Agreement.

- STANDARD OF PERFORMANCE

  - The Service Provider expressly acknowledges that it has reviewed the terms of the Customer Specifications and the Customer’s Code of Conduct for Service Providers and will carry out its obligations under this Service Schedule and in accordance with the Customer Specifications and Customer’s Code of Conduct for Service Providers.

  - The Service Provider shall perform the Services exercising due care, skill and judgment and in accordance with Best Practices, the Customer Specifications and the Customer’s Code of Conduct.

- FEES

  - The Fees for this Service Schedule are set out in Appendix A: Project Schedule.

  - Payment terms for this Service Schedule are set out in Appendix A: Project Schedule.

  - All invoices for the Fees under this Service Schedule shall be submitted in accordance with the Master Service Agreement.

|  | SERVICE PROVIDER |  |
| --- | --- | --- |
| Signature: |  |  |
|  | who warrants that he is duly authorised thereto |  |
| Name: |  |  |
| Date: |  |  |
| Place: |  |  |

|  | CUSTOMER |  |
| --- | --- | --- |
| Signature: |  |  |
|  | who warrants that he is duly authorised thereto |  |
| Name: | Matthew Campbell |  |
| Date: |  |  |
| Place: | Stellenbosch |  |

- APPENDIX A PROJECT SCHEDULE

| - Municipality |  |
| --- | --- |
| - Name of Township |  |
| - Other Comments | - Area marked in yellow (below) |

- POLYGON

| Estimated number of dwellings to be connected: | XXX |
| --- | --- |
| The date on which the Service Provider must commence with the Services in the Subarea: | XXX |
| The date on or before which the Services must be completed in the Subarea (“Deadline”): | XXX |
| The penalty amount to be imposed for failure to meet the Service timelines: | Up to 5% of the Fee for Connected Dwellings after the Deadline |
| Fee and Payment Terms: | The Service Provider shall be paid R2,700 (two thousand seven hundred Rand) for each Connected Dwelling. |
| Other Terms: | Payment will only be made for Connected Dwellings, connected on the standards and specifications as shared by fibertime™ and approved in writing before commencement of project. A Connected Dwelling must be unique, meaning that not more than one set of Customer Equipment will be connected at a single dwelling. Furthermore, it means that a unique Dwelling can only be counted once for the sake of calculating number of Connected Dwellings. |
| Official Connected Dwelling count: | All Connected Dwellings which successfully passed the testing requirements will be logged on the Customer’s Nokia EasyStart system. The Connected Dwellings as per the EasyStart system will be the final and true count of Connected Dwellings. The Connected Dwelling data as per EasyStart will be shared with the Service Provider on a weekly basis. For the avoidance of doubt, the dwelling count referred to herein is a rooftop estimate, with the Service Provider to confirm electrification. |
| Wayleave conditions: | Wayleave to be issued to the Customer or any of its Affiliates. The Service Provider must ensure that all wayleaves are ceded or transferred to the Customer. If the wayleave cannot be transferred, the wayleave must be issued directly in the name of the Customer. |
| Any specific conditions pertaining to the Subarea: | N/A |
| Frequency of which build status updates are to be provided: | The Service Provider is required to use the field applications and systems provided by the Customer. Furthermore, the Service Provider is required to provide weekly updates on the build status to the Customer in writing. |

- APPENDIX B COMPLETION CHECKLIST

Payment will only be made for Connected Dwellings. The Service Provider is required to follow the processes and standards provided by fibertime through written communication.

A Completion Checklist is required for a Dwelling Unit to be considered a Connected Dwelling. The following outlines the requirements a Service Provider must met in order to receive a signed off Compliance Checklist from the Customer.

Customer installation requirements:

Connected Dwelling has completed the following process:

      - Physical installation (Note 1); with

      - An Optical Network Terminal (“ONT”) Activated via Nokia EasyStart (Note 2); completed with

      - A Mobile Application submission (Note 3)

Notes:

- Physical installation:

- Only residents and businesses that have signed-up for the installation will receive an installation. The details will either be captured by the home permission teams via the Mobile Application (only on paper if specifically instructed by the Customer to do so). For the Home sign-up process, refer to the Customer field operations standards.

- The installation must be according to the approved Customer Specifications.

- Customer installation manuals to be shared with Service Provider:

- Separate manuals for formal (brick & mortar), informal (corrugated metal sheeting) and RDP houses.

- Multi-Dwelling Units (“MDU’s”) to be handled on a case-by-case basis between the Service Provider and Customer.

- Should a dwelling type not be covered by any of the above, the Service Provider must inform the Customer. Within 10 (ten) business days, the Customer will provide guidelines on the installation method and requirements.

- Service Provider to ensure installation teams undergo the required training on how to install according to Customer standards; and

- Service Provider to ensure controls are in place for teams to adhere to the required standards and specifications as outlined in the Service Schedules.

- Service Provider to complete Customer Home Installations Quality Control Check sheet and submit these with handover document pack.

- Nokia ONT is activated via Nokia Easy Start

- Once ONT is installed, ensure that the ONT is activated via Nokia Easy Start (web application) to ensure that it is connected to the Customer Network.

- Nokia EasyStart manual will be shared with Service Provider.

- Nokia EasyStart ensures that the ONT is only activated if the light level at provisioning is within the acceptable budget light level allocated to the Dwelling

- Service Provider must be able to verify that each installation is activated upon successful activation on the web application.

- Confirmation will be received for each successful connection.

- Installation captured on mobile application.

- Installation team captures and submits the required before and after photos and submits on mobile application.

- End User must sign consent form on the mobile application.

- Service Provider does quality assurance to ensure that installation teams have adhered to required installation standards shared by Customer.

- Once approved by the Service Provider, the Service Provider submits entries to Customer for Quality Control review.

- Approvals by Customer must form part of the handover document pack submitted by the Service Provider.

| FTN – QCCS – 1.0 |  |
| --- | --- |
| CIVIL WORKS - QUALITY CONTROL CHECK SHEET |  |  |  |  |  |  |  |  |  |  |
| TRENCHING |  |  |  |  |  |  |  |  |  |  |
| Project name |  |  |  |  |  |  |  |  |  |  |
| Zone |  |  |  |  |  |  |  |  |  |  |
| Manhole ID |  |  |  |  |  |  |  |  |  |  |
| Link ID |  |  |  |  |  |  |  |  |  |  |
| Date |  |  |  |  |  |  |  |  |  |  |
| 1.0 | TRENCHING |  |  |  |  |  |  |  |  |  |
| # | Description | Material |  |  |  | Work |  | Comments |  | Snag # |
| 1.1 | All trenches placed according to plan | Y |  | N |  | Y | N |  |  |  |
| 1.2 | All trench depths according to specification | Y |  | N |  | Y | N |  |  |  |
| 1.3 | All bedding done to specification | Y |  | N |  | Y | N |  |  |  |
| 1.4 | Warning tape placed correctly | Y |  | N |  | Y | N |  |  |  |
| 1.5 | All compaction done correctly | Y |  | N |  | Y | N |  |  |  |
| 1.6 | External lab results for each road layer work constructed based on council requirements | Y |  | N |  | Y | N |  |  |  |
| 1.7 | All DCP within accepted tolerance | Y |  | N |  | Y | N |  |  |  |
| 1.8 | Reinstatement done correctly | Y |  | N |  | Y | N |  |  |  |
| 1.9 | Rubble removed from site | Y |  | N |  | Y | N |  |  |  |
| 1.10 | Survey and redline correct | Y |  | N |  | Y | N |  |  |  |
| 1.11 | All photographs recorded | Y |  | N |  | Y | N |  |  |  |
| Signatures |  |  |  |  |  |  |  |  |  |  |
| Contractor |  |  |  |  | Date |  |  |  |  |  |
| Engineer |  |  |  |  | Date |  |  |  |  |  |
| Client |  |  |  |  | Date |  |  |  |  |  |

| CIVIL WORKS - QUALITY CONTROL CHECK SHEET |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Manholes and ducts |  |  |  |  |  |  |  |  |  |  |
| Project name |  |  |  |  |  |  |  |  |  |  |
| Zone |  |  |  |  |  |  |  |  |  |  |
| Manhole ID |  |  |  |  |  |  |  |  |  |  |
| Link ID |  |  |  |  |  |  |  |  |  |  |
| Date |  |  |  |  |  |  |  |  |  |  |
| 2.0 | Manholes and ducts |  |  |  |  |  |  |  |  |  |
| # | Description | Material |  |  |  | Work |  | Comments | Snag # |
| 2.1 | Correct size manhole placed as per design | Y |  | N |  | Y | N |  |  |
| 2.2 | Location of manhole placed as per design | Y |  | N |  | Y | N |  |  |
| 2.3 | Depth of manhole correct as per design | Y |  | N |  | Y | N |  |  |
| 2.4 | Manhole cover level | Y |  | N |  | Y | N |  |  |
| 2.5 | Manhole lid-epoxy used | Y |  | N |  | Y | N |  |  |
| 2.6 | Drainage rocks(19mm diameter) installed | Y |  | N |  | Y | N |  |  |
| 2.7 | 300mm X 300mm x 300mm drainage sump | Y |  | N |  | Y | N |  |  |
| 2.8 | Ducts entry points correct | Y |  | N |  | Y | N |  |  |
| 2.9 | Duct entry points sealed with foam | Y |  | N |  | Y | N |  |  |
| 2.10 | Duct slack correct- 2m | Y |  | N |  | Y | N |  |  |
| 2.11 | End caps on spare ducts | Y |  | N |  | Y | N |  |  |
| 2.12 | Labelling on manhole and duct correct | Y |  | N |  | Y | N |  |  |
| 2.13 | Correct duct used as per design | Y |  | N |  | Y | N |  |  |
| 2.14 | Manhole clean | Y |  | N |  | Y | N |  |  |
| 2.15 | Slack management correct inside | Y |  | N |  | Y | N |  |  |
| 2.16 | Manhole lock mechanism working | Y |  | N |  | Y | N |  |  |
| 2.17 | Manhole locked after inspection | Y |  | N |  | Y | N |  |  |
| 2.18 | Any excess rubble removed from site | Y |  | N |  | Y | N |  |  |
| 2.19 | Survey and redline correct | Y |  | N |  | Y | N |  |  |
| 2.20 | All photographs recorded | Y |  | N |  | Y | N |  |  |
| Signatures |  |  |  |  |  |  |  |  |  |  |
| Contractor |  |  |  |  | Date |  |  |  |  |  |
| Engineer |  |  |  |  | Date |  |  |  |  |  |
| Client |  |  |  |  | Date |  |  |  |  |  |

| CIVIL WORKS - QUALITY CONTROL CHECK SHEET |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Directional drilling and Molling |  |  |  |  |  |  |  |  |  |
| Project name |  |  |  |  |  |  |  |  |  |
| Zone |  |  |  |  |  |  |  |  |  |
| Street ID |  |  |  |  |  |  |  |  |  |
| Link ID |  |  |  |  |  |  |  |  |  |
| Date |  |  |  |  |  |  |  |  |  |
| 3.0 | Directional drilling and Molling |  |  |  |  |  |  |  |  |
| # | Description | Material |  |  |  | Work |  | Comments | Snag # |
| 3.1 | Road reserve launch space survey | Y |  | N |  | Y | N |  |  |
| 3.2 | Scanning(GPR) – Drill plan submitted and approved | Y |  | N |  | Y | N |  |  |
| 3.3 | Wayleave services comparison on site | Y |  | N |  | Y | N |  |  |
| 3.4 | Pilot hole - identifying services | Y |  | N |  | Y | N |  |  |
| 3.5 | Drill/Launch pits- L1500mm x W800mm x D1500m or/as supplier specifications | Y |  | N |  | Y | N |  |  |
| 3.6 | Class 10 sleeve installed or/as per wayleave specification | Y |  | N |  | Y | N |  |  |
| 3.7 | Reinstatement – drill pits and site establishment area | Y |  | N |  | Y | N |  |  |
| 3.8 | Redline correct | Y |  | N |  | Y | N |  |  |
| 3.9 | All photographs recorded | Y |  | N |  | Y | N |  |  |
| Signatures |  |  |  |  |  |  |  |  |  |
| Contractor |  |  |  |  | Date |  |  |  |  |
| Engineer |  |  |  |  | Date |  |  |  |  |
| Client |  |  |  |  | Date |  |  |  |  |

| CIVIL WORKS - QUALITY CONTROL CHECK SHEET |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Poles |  |  |  |  |  |  |  |  |  |  |
| Project name |  |  |  |  |  |  |  |  |  |  |
| Zone |  |  |  |  |  |  |  |  |  |  |
| Pole ID |  |  |  |  |  |  |  |  |  |  |
| Link ID |  |  |  |  |  |  |  |  |  |  |
| Date |  |  |  |  |  |  |  |  |  |  |
| 4.0 | Poles |  |  |  |  |  |  |  |  |  |
| # | Description | Material |  |  |  | Work |  | Comments | Snag # |
| 4.1 | Ensure correct size of pole is constructed | Y |  | N |  | Y | N |  |  |
| 4.2 | Ensure various poles are planted at correct depth as per specifications | Y |  | N |  | Y | N |  |  |
| 4.3 | Ensure all poles are fitted with end-plates and strapping at both ends | Y |  | N |  | Y | N |  |  |
| 4.4 | Ensure pole handling ratios are done with sufficient personnel | Y |  | N |  | Y | N |  |  |
| 4.5 | Ensure all brackets and fittings are fastened to the poles according to the specifications | Y |  | N |  | Y | N |  |  |
| 4.6 | Ensure all poles are planted vertically with correct backfilling procedure (150mm intervals) | Y |  | N |  | Y | N |  |  |
| 4.7 | Ensure all poles have the G5 backfilling at the bottom of the hole for pole stability | Y |  | N |  | Y | N |  |  |
| 4.8 | Ensure stays are planted at direction changes - T-junctions and end-of-runs | Y |  | N |  | Y | N |  |  |
| 4.9 | Ensure poles are numbered correctly as per Labelling Standards of Fibertime Networks | Y |  | N |  | Y | N |  |  |
| 4.10 | Tree trimming completed | Y |  | N |  | Y | N |  |  |
| 4.11 | Redline and coordinates correct | Y |  | N |  | Y | N |  |  |
| 4.12 | All photographs recorded | Y |  | N |  | Y | N |  |  |
| Signatures |  |  |  |  |  |  |  |  |  |  |
| Contractor |  |  |  |  | Date |  |  |  |  |  |
| Engineer |  |  |  |  | Date |  |  |  |  |  |
| Client |  |  |  |  | Date |  |  |  |  |  |

| OPTICAL WORKS - QUALITY CONTROL CHECK SHEET |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Stringing |  |  |  |  |  |  |  |  |  |  |
| Project name |  |  |  |  |  |  |  |  |  |  |
| Zone |  |  |  |  |  |  |  |  |  |  |
| Pole ID |  |  |  |  |  |  |  |  |  |  |
| Link ID |  |  |  |  |  |  |  |  |  |  |
| Date |  |  |  |  |  |  |  |  |  |  |
| 5.0 | Stringing |  |  |  |  |  |  |  |  |  |
| # | Description | Material |  |  |  | Work |  | Comments | Snag # |
| 5.1 | Correct Cable size has been strung | Y |  | N |  | Y | N |  |  |
| 5.2 | De-coiler used for stringing | Y |  | N |  | Y | N |  |  |
| 5.3 | Sagging/ tension correct | Y |  | N |  | Y | N |  |  |
| 5.3.1 | Mini ADSS – 320N-360N | Y |  | N |  | Y | N |  |  |
| 5.3.2 | ADSS – 600N-700N | Y |  | N |  | Y | N |  |  |
| 5.4 | Correct dead end used. | Y |  | N |  | Y | N |  |  |
| 5.5 | Cable does not touch any objects | Y |  | N |  | Y | N |  |  |
| 5.6 | Slack management as per design | Y |  | N |  | Y | N |  |  |
| 5.7 | All after stringing tests received and passed | Y |  | N |  | Y | N |  |  |
| 5.8 | Redline correct |  |  |  |  |  |  |  |  |
| 5.9 | All photographs recorded | Y |  | N |  | Y | N |  |  |
| Signatures |  |  |  |  |  |  |  |  |  |  |
| Contractor |  |  |  |  | Date |  |  |  |  |  |
| Engineer |  |  |  |  | Date |  |  |  |  |  |
| Client |  |  |  |  | Date |  |  |  |  |  |

| OPTICAL WORKS - QUALITY CONTROL CHECK SHEET |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Splicing |  |  |  |  |  |  |  |  |  |  |
| Project name |  |  |  |  |  |  |  |  |  |  |
| Zone |  |  |  |  |  |  |  |  |  |  |
| Pole ID |  |  |  |  |  |  |  |  |  |  |
| Link ID |  |  |  |  |  |  |  |  |  |  |
| Fibre ID |  |  |  |  |  |  |  |  |  |  |
| Date |  |  |  |  |  |  |  |  |  |  |
| 6.0 | Splicing |  |  |  |  |  |  |  |  |  |
| # | Description | Material |  |  |  | Work |  | Comments | Snag # |
| 6.1 | Correct dome used | Y |  | N |  | Y | N |  |  |
| 6.2 | Cables labelled as per labelling standards | Y |  | N |  | Y | N |  |  |
| 6.3 | Correct cable sizes | Y |  | N |  | Y | N |  |  |
| 6.4 | Slack management from pole to ground | Y |  | N |  | Y | N |  |  |
| 6.5 | Seals tightened | Y |  | N |  | Y | N |  |  |
| 6.6 | Strength members fastened | Y |  | N |  | Y | N |  |  |
| 6.7 | Spare tubes management correct - does not twist etc | Y |  | N |  | Y | N |  |  |
| 6.8 | Transportation tube correct | Y |  | N |  | Y | N |  |  |
| 6.9 | Bare tube – sponge tape | Y |  | N |  | Y | N |  |  |
| 6.10 | Cable ties | Y |  | N |  | Y | N |  |  |
| 6.11 | Fibre coiling | Y |  | N |  | Y | N |  |  |
| 6.12 | Correct splice protector used | Y |  | N |  | Y | N |  |  |
| 6.13 | Correct fibres spliced as per splicing diagram | Y |  | N |  | Y | N |  |  |
| 6.14 | Midcoupler - dust caps | Y |  | N |  | Y | N |  |  |
| 6.15 | Redline and Splicing diagram correct | Y |  | N |  | Y | N |  |  |
| 6.16 | All photographs recorded | Y |  | N |  | Y | N |  |  |
| Signatures |  |  |  |  |  |  |  |  |  |  |
| Contractor |  |  |  |  | Date |  |  |  |  |  |
| Engineer |  |  |  |  | Date |  |  |  |  |  |
| Client |  |  |  |  | Date |  |  |  |  |  |

| OPTICAL WORKS - QUALITY CONTROL CHECK SHEET |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Testing |  |  |  |  |  |  |  |  |  |  |
| Project name |  |  |  |  |  |  |  |  |  |  |
| Zone |  |  |  |  |  |  |  |  |  |  |
| Location A and B |  |  |  |  |  |  |  |  |  |  |
| Link ID |  |  |  |  |  |  |  |  |  |  |
| Fibre ID |  |  |  |  |  |  |  |  |  |  |
| Date |  |  |  |  |  |  |  |  |  |  |
| 7.0 | Testing |  |  |  |  |  |  |  |  |  |
| # | Description | Material |  |  |  | Work |  | Comments | Snag # |
| 7.1 | Dust caps in place. | Y |  | N |  | Y | N |  |  |
| 7.1.1 | Midcouplers | Y |  | N |  | Y | N |  |  |
| 7.1.2 | Patch leads | Y |  | N |  | Y | N |  |  |
| 7.2 | Use one click cleaners to clean; | Y |  | N |  | Y | N |  |  |
| 7.2.1 | Midcouplers | Y |  | N |  | Y | N |  |  |
| 7.2.2 | Patch leads | Y |  | N |  | Y | N |  |  |
| 7.3 | Testing equipment setup as per FTN testing specifications | Y |  | N |  | Y | N |  |  |
| 7.3.1 | Job ID | Y |  | N |  | Y | N |  |  |
| 7.3.2 | Fibre ID | Y |  | N |  | Y | N |  |  |
| 7.3.3 | Location A and B | Y |  | N |  | Y | N |  |  |
| 7.3.4 | Link ID | Y |  | N |  | Y | N |  |  |
| 7.3.5 | Thresholds | Y |  | N |  | Y | N |  |  |
| 7.3.6 | Operator | Y |  | N |  | Y | N |  |  |
| 7.3.7 | Date and time | Y |  | N |  | Y | N |  |  |
| 7.4 | Testing equipment referenced | Y |  | N |  | Y | N |  |  |
| 7.5 | Launch lead | Y |  | N |  | Y | N |  |  |
| 7.6 | All tests passed | Y |  | N |  | Y | N |  |  |
| Signatures |  |  |  |  |  |  |  |  |  |  |
| Contractor |  |  |  |  | Date |  |  |  |  |  |
| Engineer |  |  |  |  | Date |  |  |  |  |  |
| Client |  |  |  |  | Date |  |  |  |  |  |

| OPTICAL WORKS - QUALITY CONTROL CHECK SHEET |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Home installations |  |  |  |  |  |  |  |  |  |  |
| Project name |  |  |  |  |  |  |  |  |  |  |
| Zone |  |  |  |  |  |  |  |  |  |  |
| Pole ID |  |  |  |  |  |  |  |  |  |  |
| Link ID |  |  |  |  |  |  |  |  |  |  |
| Fibre ID |  |  |  |  |  |  |  |  |  |  |
| Date |  |  |  |  |  |  |  |  |  |  |
| 8.0 | Home installations |  |  |  |  |  |  |  |  |  |
| # | Description | Material |  |  |  | Work |  | Comments | Snag # |
| 8.1 | Drops patched In sequence at dome. | Y |  | N |  | Y | N |  |  |
| 8.2 | Drops labelled correctly as per fibertime labelling specifications. | Y |  | N |  | Y | N |  |  |
| 8.3 | Correct drop number used as per design. | Y |  | N |  | Y | N |  |  |
| 8.4 | Slack from dome to halo correct. | Y |  | N |  | Y | N |  |  |
| 8.5 | Slack from dome to slack bracket correct. | Y |  | N |  | Y | N |  |  |
| 8.6 | Dead-ends completely wrapped at dome side | Y |  | N |  | Y | N |  |  |
| 8.7 | Dead-ends completely wrapped at home side. | Y |  | N |  | Y | N |  |  |
| 8.8 | Spans from dome to home - drops does not touch anything. | Y |  | N |  | Y | N |  |  |
| 8.9 | Bending radius at dead - ends correct. | Y |  | N |  | Y | N |  |  |
| 8.10 | From pigtail screw to house entry, cable makes small loop to prevent water from entering the house. | Y |  | N |  | Y | N |  |  |
| 8.11 | Pigtail screw entry point sealed with Silicone- UV rated | Y |  | N |  | Y | N |  |  |
| 8.12 | House entry - gland, duct sealed. | Y |  | N |  | Y | N |  |  |
| 8.13 | Fibre run Inside house neat and secured - glue or saddles. | Y |  | N |  | Y | N |  |  |
| 8.14 | ONT/Gizzu bracket level. | Y |  | N |  | Y | N |  |  |
| 8.15 | Drop cable slack correct. | Y |  | N |  | Y | N |  |  |
| 8.16 | ONT sticker and label on. | Y |  | N |  | Y | N |  |  |
| 8.17 | Gizzu set on 12V. | Y |  | N |  | Y | N |  |  |
| 8.18 | ONT activated. | Y |  | N |  | Y | N |  |  |
| 8.19 | All data captured op web application | Y |  | N |  | Y | N |  |  |
| 8.20 | All photographs recorded | Y |  | N |  | Y | N |  |  |
| Signatures |  |  |  |  |  |  |  |  |  |  |
| Contractor |  |  |  |  | Date |  |  |  |  |  |
| Engineer |  |  |  |  | Date |  |  |  |  |  |
| Client |  |  |  |  | Date |  |  |  |  |  |

- APPENDIX C APPROVED SUPPLIER LIST

The Service Provider may acquire approved Outside Plant (“OSP”) materials from any of the following approved Suppliers:

  - FTTX

  - Average

  - CFS

- APPENDIX D CUSTOMER CODE OF CONDUCT FOR SERVICE PROVIDERS